OrgIQ-SmartStructure: What How Why
Checklist for Successful Changes

Author:	Danilo Assmann
Status:	released
Version:	1.0.0 (build 110)
Date:	2025-02-11
Copyright:	© 2024. This work is openly licensed via CC BY 4.0 BY SA

Purpose
This checklist has been developed over many years. Well over 10 years. And initially it was only about the question of what is contained in the proven project management standards on the subject of “Purpose”—i.e. the “Why”. What can we learn from the experts on this topic and how can we package it in a practical and pragmatic way?
There are an incredible number of good standards on the subject of project management, but especially in the concept of the solution—i.e. the conscious, step-by-step development of an idea—many approaches were too vague and expensive. There were also blind spots that took their toll in practice and made life difficult or caused projects[1] to fail.
[1] Project is a change hub on an existing solution. A change or transformation. It's not about the size.
So it’s not about replacing standards, but about adding a small, pragmatic tool. In doing so, we are following the mindset of leadership rather than traditional management. Nevertheless, using the checklist can be helpful in all contexts. Try it out and add to and improve it.
Thank you.
# Summary
Procedure: First fill out the questions, then transfer them to the summary.
It is up to you whether you actually go through the questions in an interview. This can work well within an organization with a high level of trust. Otherwise, this checklist is more for reflection. With this guide, you can easily hear what is being said and what is omitted. Where is the focus and where is there ambiguity in the assignment. Then you can also ask specific questions and clarify.
Note: Ambiguity is not a bad thing, it just increases the statistical spread. We often cannot eliminate it at the beginning, we just need to be aware of it.
User Story(s): As <Role> I want <Goal/Wish>, to <Value>.

Idea/Topic	xxx
Purpose (Why) and Effect	One-liner ... / ...
Motivation (What was the pain?)	...
Overall clarity
Project frame (How)	...
Goals (What)/Non-Goals	... / ... / ...
Acceptance Criteria (How to check)	... / ... / ...
Value / Effort / Time frame / Workload	… / … / … / …

Target Group/ Customer	... / ...	Interested in/ Contribution	... / ...

Dependencies/ Impediments/ Constraints	... / ... / ...

# Question List for Project Definition
## Understanding the Desired Solution
Figure 1: Visualization of what, how and why. What: Project result. How: The project process. Why: The effect of the project result. If the Why is not clear, there is a very high risk that everything else is wrong and not “goal-oriented”.
OrgIQ thinks in “solutions”. In a solution, every project is either the application of a solution for a customer, or a change in the sense of an improvement to the solution itself. This checklist focuses on changes because we are open to the future and have uncertainty there. In Solutions, we have the advantage that there is always a purpose. And the change (the why) must serve this purpose. This is often very difficult to find out in other contexts because there are only implicit or unconscious models. (And we don't like to talk about it because we don't want to show uncertainty. We also need to be careful when asking questions because we don't want to start with a loss of face).
###### WHAT (Project Result)
What exactly do you want? What does it look like? à Are there any good examples/mock-ups/prototypes/sketches?
Here we want to understand how clear the solution is for the client. Should we build his solution, or should we solve a problem and are still free in our approach and concept? The chosen scenario is also derived from this (see part 2.3).
Find out whether it is a “heartfelt concern”: with these topics, there is very little freedom. A lot of consultation and feedback is necessary. Possibly also a high priority.
  - Are there already concrete ideas (at What and How level)?
  - Is it a matter of the heart or rather “necessary”? (is it the client’s own/personal concern?)
- What is your target group? (customer, area, solution, ...)
- What do you value in the solution? (Slim, fast, robust, etc.?)
Important!!! Find out what constitutes the optimal solution (OrgIQ standard is the “minimum principle” or “maximize the work not done”). Then also set up a mechanism for this so that you stay on track. Possibly an external team checker.
- What should the solution contain? (Roll-out, training, etc. included?)
- “How sure are you that this is the final solution (target scenario)?” (Scale 1..10; 10 is completely certain)
Implicit question about change VAC/frequency or how mature and stable the wishes/concepts are.
###### HOW (Project Procedure; Work Packages, Milestones and Sequence)
Do you have an idea of what the solution should look like? (Fixed solution path, or are we free?)
If the solution (project process) is known: ask explicitly for the solution because no alternative is desired.
  - “How sure are you that this is the final solution (process)?” (Scale 1..10; 10 is completely certain)
Test and challenge here too; prototype, final version?
- What are the absolute core elements (pegs)? (Features with clear priorities)
- What dependencies and synergies are you aware of?
  - What conflicts of interest are you aware of?
  - Is there a hidden agenda? (this question clearly shows that I need to hear the answer!)
Are there dependencies, impediments or constraints?
- What should it cost? (rough estimate; budget; see information on Solution & Budget)
- Time frame: Until when?
If a time estimate is available: Does it include buffers? Has the rollout been factored in?
###### WHY (Project effect, the benefit)
Why do we (as an organization/system) want the project? What will be better after the project?
What effect do you want?
Important: Recognize here whether it is about a paradigm shift! These are the critical issues because we can’t ask the customers/the target organization.
Key idea here from Henry Ford: “If I had asked the customers what they wanted, they would have answered ‘faster carriages/horses’.” So sometimes you should talk to the end customers, sometimes the rethink has to take place beforehand. But rethinking should then also be part of the project. “Change of perspective” work package. The iPhone effect doesn’t always happen.
Note: there can be different (several independent) effects!
What happens (does it cost us) if we do nothing?
Another way to understand the benefits. We get a comparison scenario. This makes the necessary effects/benefits visible. We know what needs to be achieved.
It also gives us a feeling of whether it is really necessary or just “nice”.
- What is it worth to you? (Value calculation about added value or savings) [see Tools]
  - Include opportunity costs here too. If I opt for one solution, then I can’t do anything else. What does it cost me? What am I missing out on? We can also compare alternative approaches.
## Evaluation of the built solution (Acceptance Criteria)
###### WHAT
- How much and how well should be converted by when (partial solution becomes active)?
  - Time, type and scope of the solution (order of magnitude, scope, percentage...), → e.g. “What should be different in one month/one year?” (Depending on the scope of the solution, if needed at all.) Only if incremental/iterative visible solution.
Possible implementations using the example “Acceleration of xyz”:
1) Slides were shown
2) We know (however) that some people have actually understood the slides (which is not trivial)
3) There are people who also implement some of it
4) We can see minimal effects (for this we needed a baseline beforehand (!))
5) We can see effects that are actually related to the information/instruction (chain of effects)
6) "by feel" (then measure the problem first to understand whether there really is a problem)
###### HOW
- Review by client/deputy
  - Note: create a baseline beforehand (this is almost always forgotten; the challenge is to find the right time: We still need the old state, but we need to have understood the effect of the change well enough to measure the right thing)
- Feedback from the affected organization
  - “What was understood?”
  - “What was accepted and implemented by the organization?”
Note: For process topics, integrate changes in audits, reviews, checks, quality gates, and metrics!
###### WHY
- Time and type of occurrence of the effect (if effect exists!)
  - How and when do we evaluate the effect?
  - How do we ensure that the observed effect comes from the change and not from “niceness”?
- Are interim targets sensible? (Milestones)
  - If so, when and which ones?
## Project Process and Organization for Solution
###### HOW
- Derive scenario
- Define team
  Figure 1: We differentiate two basic approaches. Feedback driven vs. DoD (Defintion-of-Done) or criteria based.
  - Who is our primary contact (external customer? product owner? business owner? solution owner? CEO?)?
  - Further distribution of roles: client, stakeholders/interested parties, customers [there is enough information on this in the relevant standards].
  - Team members: Who is part of the team?
Can also be people from other areas. Our wishes can be included here, but also suggestions from the client. This is where the network comes into play.
- How often does the project team meet (participants depending on the scenario)?
- Communication of progress and interim results:
  - How do we update clients? What do we show? (Prototype, slides, concept, training plan, etc.) Can change in the course of the project; i.e. what is good and when?)
  - At what distance and how? Continuously, regularly or sporadically?
- Continuous à via tools (Temas, Jira, Click-up, ...) - “silent” group member?
- Regularly à meeting or by e-mail?
- Sporadically à on request and then also via the selected platform (Teams, e-mail, etc.)
Enter probability of success (scale 1..10; 10 is very certain success)
Level is decided by the team (gut feeling assessment, consideration of external framework conditions); depending on how clearly and completely the questions were answered; number and size of changes (implicit or explicit)
The risk level is checked implicitly here; we only do it positively. Low values mean a high risk and can lead to opps/risks (if necessary, hold a workshop on the topic and enter the results).